## Phase 1 Tasks
UI UX Process | Target
Define the goals and objectives of your site (UX Writing) | Phase 1
Create a wireframe | Phase1.1
Organize your content and create a content list | Phase 2
Create a task list. Visualize what you need to do at every stage of the site creation process | Phase 2.1
Set a timeline | 40-80 hours(approx)
Establish a budget | 25-30 $/hrs
Assemble a team | Product + Tech
Create a basic design and Prototype | Phase 3
Final design | Phase 4
Frontend Start in parallel as soon as design template and creative are fixed | Phase1
AMC(maintenance, bug fixes,content changes, logic changes, re-structuring, modifications etc.) | 20k/month

## Scope of project
Website Development - building of web pages from scratch to high level (Suitable both for WEB and Mobile Site) | Total no. of pages- 22 to 25
Website SiteMap
Main Navigation
Tours
Stories
Social Media
3 Party Pages
Contact Us
Partner Page
About Us
News and Media
Career
Privacy Policy
Booking Flow
Payment View/ Success and Failure View
API Development from scratch which will include 2end point data flow:
--Saving data from dashboard to DB.
--Fetching Data from DB to website.
--Cancellation Flow API, Booking Flow API, Seat Booking and Reservation
Exclude-
Multiple web page structural changes won't be entertained once design is fixed from client end.
DASHBOARD :-
UI platform which will help user's for the following:
Text Updates
Video Updates
Image Updates
LOGIN Functionality- for email id's you will provide us, we will give access to those id's only for dashboard
Exclude:
Page structure can not be changed from dashboard.
For login, only email and password verification take place. Roles are not managed.
All hosting , server, DB setup cost , AWS instance cost own by client
Note: Need a discussion****
Content - such as text, images, videos will be provided by the client
Hosting information
Payment Gateway - Need to be specified (which 1)
Language barrier - queries
Technology Involves:
React js
Javascript
AWS Amplify
Java
Final quote : 5.4 Lac

## Technology
Technology | React Js
Hosting Service | AWS or any other?
Number of Pages (Phase-1) | Approx - 22 -25 pages
(per page 10 -15 hrs) - depending upon structure,content, assets and design
Require Videos / Media/ Images for buses, travellers etc, media
Require link for media and news
Establish a budget | $25-$30 per hours
Total hours | ~225-240 Hours
Phase-1 and Beta Release | Setting Up project and dependencies
Basic structuring of pages as per design
Pages: Home page, Booking Flow pages(min 6 to 7 views), Main Navigation Pages, Tours Pages, Storeies, Social Media Page, 3Party Ads, Contact Page, About Us, Misc.
Backend | Mostly In java as Payment is involved (security is concerened)
Establish a budget | $25-$30 per hours
Total hours | ~40-100 Hours
Front End | 2.4 Lac
Back End | 1.5 Lac
Design | 1.5 Lac